## Sheet1
Given: |  | table of plot
project total estimated budget(planned value) | 10000 hr | DATE | Planned Value | actual cost | earned value
project progress | 55% | 0 | 0 | 0 | 0
team size | 5 | 7.5 | 5000 | 7000 | 5500
team logged hours (actual value) | 7000 hr | 15 | 10000
earned value | 5500 hr
Required: | Solution:
is the project over budget? If yes by how many hours? | yes we are over the budget by 1500 (7000-5500)
is the project delayed? If yes by how many hours? | no we are ahead by 5%(500hr)
plot achart that compares the actual cost with the corresponding earning value?
Before plot:
what is the expected life time of the project?
*assume one engineer in one month spends 150 working hr and team size is 5
*given life time of the project is 10,000 hr
*life time of the project = 10,000/(5x150)=13.33 month
*we add 10% due to contangency, life time of project become 15 month
where are we in the life time of the project?
*assume we are at 50% of project life time at the month 7.5
*at 50% of project life time the progress is 55%